Shielding action list

A-frame

- Reinforcement of A-frame

  - Design work	Wim

  - Calculation, calculation report	Dimi

  - Call Benoit to get the approval report	Raphael

  - Order materials	Dimi/Wim/Erik

  - Welding of the reinforcement plates	Alain

    - Order a 3rd bobine of filler material	Raphael

  - Weld bock for survey holes on the Feet for survey target	Alain/Wim

  - Send to 180 the stainless steel block of the feet	Dimi

- A-frame test

  - Design the necessary tooling	Wim

  - Order the material (plate)	Dimi

  - Machining of the plates	Dimi

  - Transport the traction bars to 180 with the nuts and washers	Dimi/William

  - Collect the jack from Fred. Rosset with the pump	William

  - Collect the feet contact block	William

  - Load test ; 135 T x 1.5 = 202.5 T	Dimi

- Temporary connection to ECT

  - Design of the connection	Wim/Raphael

  - Order materials (plate, threaded bar, springs, nut, washer)	Dimi

  - Machining of the aluminum plate	Dimi

  - Send the drawing to ECT team to drill them	Wim/Raphael

- Installation procedure

  - Write down the procedure of installation and access for adjustments	Wim

  - Provide the final layout of the A-frame position	Wim

  - Verify that the bolts for the A-frame is received (order)	Jan/Dimi

    - Design the new bolts M50	Wim

    - Order Material, bolts and washers	Dimi

    - Machine the bolts and nuts	Raphael

  - Check if a plate is needed at the extremity of the rail (Yes for side A) 	Wim/Raphael

    - Order the plate	Dimi

    - Machine the plate	Dimi

  - Store in CDD the updated drawing of the A-frame	Wim

  - Store in CDD the positioning layout drawing 	Wim

  - Store in CDD the installation drawing 	Wim

JF beams

- Order locking nuts for the jacks	Jan

  - Check delivery status for nuts	Jan (Urgent)

- Order swivel heads for the jacks	Raphael

- Machine the centering washer for the Jack positioning	Dimi

- Design stopper for positioning on HF rails	Jan/Raphael

- Design stopper for positioning the HF truck on guiding rails	Petr

- Finalized the design of the jacks extension for JFC1	Jan

  - Send in production the extension	Raphael

- Finalized the design of the jacks extension for Hexagonal shielding	Jan

  - Send in production the extension	Raphael

- Bring to 180 the connection bolts between the jack and the JF beams	Vincent

- Finalized the design of the jacks extension	Jan

- Assembly work

  - Provide assembly drawing	Jan

  - Assemble the JF beams	William

  - Drill holes for sliding pads	William/Survey

Sliding pads

- Design of the sliding system for the shielding JFC1	Jan

- Transport the sliding pads with cylinder to 180	William

- Machine the sliding block for Teflon fixation	Jan/Dimi

- Order Stainless steel sliding surface	Dimi

- Order and machine the pin for the swivel heads	Jan/Dimi

- Assembly	William/Dimi

Extension table

- Design the Extension table	Jan

- Transport of HEA700 beams to 180	Dimi

  - Clean HEA 700	Topilin

  - Cut the beams	Vito

  - Transport HEA 200 beams to 180 and cut	William

- Order connection plate for beam welding	Jan/Dimi

- Write down results of the calculation under 300T compression load and during lifting with the crane	Jan

- Assembly

  - Grinding surface for welding	Vito

  - Order filler materials	Raphael

  - Preparation work – Spot welding for positionning	Vito

  - Position with survey team before welding 	William

  - Welding the structure	Alain

  - Provide an assembly drawing showing the altitude	Jan

JFC1

- Design the stroppers	Petr

- Machining of the stopping (X-Z) surfaces	Christian

- Ordering materials for the X-Z stoppers	Petr/Dimi

  - Machining the stoppers	Dimi

- Machining of the mono-bloc for the X-Z stoppers	?

  - (Drill hole for platform)	?

- Order painting for JFC1/JFC2/JFC3	Vincent/Jan

  - Painting	?

- Procedure for lowering down the JFC1	Petr

  - Inclination on surface	Patrick

  - Position of the HF truck	Petr

  - Movement of the truck	Petr

  - Check conflict with other systems	Petr/Tatiana

  - Check that the truck can be taken out of the trench when the shielding is in place	Petr

- Define the filling material at the location of the rollers	Jan

  - Order filling materials and machining	Dimi

- Finalized the design of the Beam Pipe access platform. Split the platform in 2 to allow the possibility to use the platform when JFC2 is in installed	Erik

  - Provide production drawing for the platform	Erik

  - Provide drawing for drilling of the JFC1	Erik

  - Drill holes in the JFC1 for platform positioning	Christian/Armen

  - Drill holes M12 in JFC1 for survey tools	Christian/Armen

  - Change the bolts M4 to M8 for side cover	?

JFC2/3

- Procedure for lowering down the JFC2	Petr

  - Inclination on surface	Patrick

  - Positioning on the JFC2/3	Petr

  - Check conflict with other systems	Petr/Tatiana

- Positioning on JFC1 (guidance)	Petr

Hexagonal shielding

- Top hexagonal pieces

  - Get drawings for mechanical adjustment of TAS	Vincent

    - Check the consequences of an offset of the top hexagonal pieces	Jan

  - Verify that the hexagonal pieces are symmetric	Raphael/Vincent

  - Find a solution to cut the extra materials that avoid a good contact between top and bottom hexagonal shielding	Raphael

Installation work

- Scheduling of the installation	Patrick